## Outline (hidden)
CRP | DMC Overview | Angio Case | Instance | What's not there | DMC | Staging Area | Data Validation | Scenarios
(Greg)
Objectives | SCP Family | Architecture | DM | All attributes | UI | Structure | History Qty Match | Forecast Source change
Schedule |  | Data Flow | -Access | UOM |  | Demarkation | Item Match | Item Change
Roles |  | What's not there |  | Notes | Dimensions | - DMC ONLY | Customer/Sites match | Booking Changes - Dates, Qty, Cancellation, Creation
Artifacts |  |  | EBS DEV | EBS Load | Levels, Attribute |  | Monthly buckets | Item transition GLF >> QBY
What's not there |  |  |  |  | Measures |  | PTO Items | Forecast generation
[5 empty] | Tables/Reports |  | Capital Items | Fcst Models used
[7 empty] | Forecast Source | Adjust History and re-run Fcst
Mid-cycle History refresh
Metrics
Archiving
Marketing Override Process
Forecast to EBS
EBS Load
Objective
  Familiarize yourself with DM Cloud application
  Validate
    Data Modeling
    Process
    Data Flow
  Check the limited development objects already in place
  Execute test scenarios
  Identify issues
Schedule
  2 weeks (Gantt including milestones within CRP)
  How many sessions?
  Agenda
Artifacts
  CRP Issue Log
  DM Cloud Test Instance
  DEV EBS
Roles
  Ankit - Coordinating sessions, Managing issue log, requirement review
  Goutham and Prurushottam – Continue with configurations, development; Support CRP sessions
  Gaurav - Design discussions
  Angio team - Validation

## Daywise (hidden)
Date | Location | Participants | Duration | Agenda
Day 1
2020-03-03 | PE Conference Room | Angio Team Triniti Team | 1 | 1. User creation 2. Access management 3. Introduction to Supply chain planning and Oracle DM Cloud work Area
2020-03-03 | PE Conference Room | Angio Team Triniti Team | 1 | 1. Work with Page Layouts 2. Overview of Supply Chain Planning Plan Types
2020-03-03 | PE Conference Room | Angio Team Triniti Team | 1 | 1. Planning Analytics 2. Dimensions and Dimension Catalogs 3. Measure Catalog walk-thru
2020-03-03 | PE Conference Room | Angio Team Triniti Team | 1.5 | 1. Levels and Attributes 2. Measures in Supply Chain Planning 3. Configuring Demand Plan
2020-03-03 | PE Conference Room | Angio Team Triniti Team | 0.5 | Capturing and discussing the issues identified during the day
Day 2
2020-03-04 | PE Conference Room | Angio Team Triniti Team | 1 | 1. Create and Manage DM Cloud Tables, Graphs 2. Manage Measure Data in Tables 3. View the Audit Trail for a Measure
2020-03-04 | PE Conference Room | Angio Team Triniti Team | 2 | 1. Configuring new table 2. Adding different type of filters in the tables
2020-03-04 | PE Conference Room | Angio Team Triniti Team | 1 | 1. Angio specific setups and data validation: a) Angio Time, Product, Geo, Customer Dimensions b) Angio specific measures c) Angio tables
2020-03-04 | PE Conference Room | Angio Team Triniti Team | 1 | 1. Review of the data: a) Angio History Analysis - By Item and Org b) Angio History and Forecast Analysis - By GBU and Org c) Angio Forecast Analysis - By Customer
2020-03-04 | PE Conference Room | Angio Team Triniti Team | 0.5 | Capturing and discussing the issues identified during the day
Day 3
2020-03-05 | PE Conference Room | Angio Team Triniti Team | 2 | Data Review continued
2020-03-05 | PE Conference Room | Angio Team Triniti Team | 2 | 1. NPI and Chaining process 2. What-If analysis - Simulation process
2020-03-05 | PE Conference Room | Angio Team Triniti Team | 1 | Capturing and discussing the issues identified during the day
Day 4
2020-03-06 | PE Conference Room | Angio Team Triniti Team | 1 | Data Review continued
2020-03-06 | PE Conference Room | Angio Team Triniti Team | 1 | Review the final issue list

## Header
AIM
TE.040 System Test Scripts
Triniti
Author | XX YY
Creation Date | 2020-12-01
Last Update Date | 2021-02-12
Version | 1.1
Change Record
Date | Author | Version | Change Reference
2020-12-01 | XX YY | 1 | New Document. No Previous Document
2020-12-01 | XX YY | 1.1 | Adding test scripts for 20D Upgrade and Previous version opt-in expiration test cases
2021-02-12 | XX YY | 1.2 | Adding test scripts for 20D Upgrade and Previous version opt-in expiration test cases

## 20D Upgrade
Test Case ID | Test Scenario Type | Category | Test Scenario Description | Expected Result | When | Who | Actual Results (Pass/Fail) | Time Taken | Remarks
<20D-1> | Regression | <Integration> | <Testing the integration created between Legacy system and Cloud environment> | <Integration should working as expected> | <Execution Date> | <Resource> | <Pass/Fail> | <Time Taken> | <Remark>
<20D-2> | Upgrade Specific | <Requirement> | <Testing the new feature coming up in the upgrade> | <New feature working as expected> | <Execution Date> | <Resource> | <Pass/Fail> | <Time Taken> | <Remark>
<20C-3> | Opt-In expiration | <Requirement> | <Testing Opt-In expiration features> | <Opt-In expiration features working as expected> | <Execution Date> | <Resource> | <Pass/Fail> | <Time Taken> | <Remark>

## 21A Upgrade
Test Case ID | Test Scenario Type | Category | Test Scenario Description | Expected Result | When | Who | Actual Results (Pass/Fail) | Time Taken | Remarks
<21A-1> | Regression | <Integration> | <Testing the integration created between Legacy system and Cloud environment> | <Integration should working as expected> | <Execution Date> | <Resource> | <Pass/Fail> | <Time Taken> | <Remark>
<21A-2> | Upgrade Specific | <Requirement> | <Testing the new feature coming up in the upgrade> | <New feature working as expected> | <Execution Date> | <Resource> | <Pass/Fail> | <Time Taken> | <Remark>
<20D-3> | Opt-In expiration | <Requirement> | <Testing Opt-In expiration features> | <Opt-In expiration features working as expected> | <Execution Date> | <Resource> | <Pass/Fail> | <Time Taken> | <Remark>